## Лист1
|  |  | Build number | 1.0 |  |  |  | 1.0
|  |  | Test type | AT |  |  |  | MAT/AT |  |  |  | Cases Run | Not implemented
|  |  | Test date | 22.09.2022-07.102022 |  |  |  | 22.09.2022-07.102022 |  |  |  | Passed
|  |  | Tester | A.Shkurat |  |  |  | A.Shkurat |  |  |  | Failed
|  |  | Project Environment | https://bccp.demohoster.com/ |  |  |  | https://bccp.demohoster.com/ |  |  |  | Not available
|  |  | Operating System | Windows 10 х64 |  |  |  | Windows 10 х64 |  |  |  | Not implemented
|  |  | Browser | Google Chrome ver.105.0.5195.127 |  |  |  | Mozilla Firefox 48.0.2 |  |  |  | Not tested
|  |  |  | Test Cases Statistics |  |  |  | Test Cases Statistics
Precondition: 1. Tests are performed on accounts: General, Operator, Corporate, Imanager. 2. Password (for all accounts): test123 |  |  | Total Test Cases Run | 102 |  |  | 100% | 93 |  |  | 100%
|  |  | Test Cases Passed | 70 |  |  | 68.63% | 38 |  |  | 40.86%
|  |  | Test Cases Failed | 30 |  |  | 29.41% | 18 |  |  | 19.35%
|  |  | Test Cases Not available | 2 |  |  | 1.961% | 37 |  |  | 39.78%
|  |  | Test Cases Not implemented | 1 |  |  |  | 1
|  |  | Test Cases Not tested | 28 |  |  |  | 37
Module
Test Type | Functionality | Actions | Expected Result | Result | Issues | Comment | Tester | Result | Issues | Comment | Tester
Mod: Dashboard | Mod:Dashboard
Smoke |  | FUN: make sure that the page tab opens | the tab on the page is loaded correctly | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: check font consistency | all fonts are the same style | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: check text height and width uniformity | the text of section headings is the same height; the text in the sections is the same | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: сheck text alignment | text is left aligned | Failed | QATC-674332 | the text is not left aligned | A.Shkurat | Failed | QATC-674332 | the text is not left aligned | A.Shkurat
AT |  | GUI: make sure all links are underlined and blue | all links are underlined and blue | Failed | QATC-674408 | links are grayed out | A.Shkurat | Failed | QATC-674408 | links are grayed out | A.Shkurat
AT |  | GUI: spell check | the first word of the titles of sections and links is written with a capital letter, the rest of the words - with a lowercase | Failed | QATC-677887 | all words in links and section names are written with a capital letter. | A.Shkurat | Failed | QATC-677887 | all words in links and section names are written with a capital letter. | A.Shkurat
Smoke | Fun: Notifications | FUN: check if notifications are displayed | notifications are displayed | Passed |  |  | A.Shkurat | Failed | QATC-677077 | the views are not displayed | A.Shkurat
MAT |  | FUN:Check that the changes madewithin one account do not affect other accounts | the changes madewithin one account do not affect other accounts | Failed | QATC-674660 | manipulations made within one account are reflected by the same actions on other accounts available for testing. | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: make sure that after pressing the [x] button, the notification disappears | the notification disappears | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: сheck the [x] button in notifications | the system moves the notification to the Viewed Notifications section. | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: check that the cursor changes its appearance when hovering over the [x] button | the cursor changes | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: check that the [x] button is highlighted when the cursor hovers over it | the [x] button is highlighted | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: make sure that the text does not go beyond the working area of the notification | the text does not go beyond the working area of the notification | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: check that there are no grammatical, syntactic and punctuation errors in the notification | text without error | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: check that the background color of the notification frame matches "blue". | The background color of the notification frame corresponds to "blue". | Failed | QATC-674592 | gray background color of the notification frame | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | GUI: check that the correct date and time is displayed in the notification(MM/DD/YYYY) | the date and time are displayed correctly (MM/DD/YYYY) | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: check that the notification frames has the same size | notification frames has the same size | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
Link: See Viewed Notifications
MAT |  | FUN: check that by clicking on the link the system opens a tab with all the latest notifications | system opens a tab with all the latest notifications | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT |  | FUN: check that notifications are marked as viewed | notifications are marked as viewed | Passed |  |  | A.Shkurat | Not available |  | notifications are not in the database | A.Shkurat
MAT |  | FUN: check that the read notifications are sorted by time in descending order. | read notifications are sorted by time in descending order. | Passed |  |  | A.Shkurat | Not available |  | notifications are not in the database | A.Shkurat
MAT |  | FUN: check that the "View Viewed Notifications" link has been replaced with the "Close Viewed Notifications" link. | "View Viewed Notifications" link has been replaced with the "Close Viewed Notifications" link. | Failed | QATC-675478 | the link is not replaced | A.Shkurat | Failed | QATC-675478 | the link is not replaced | A.Shkurat
MAT |  | FUN: Check that when you click on the link again, it collapses | it collapses | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT |  | FUN: сheck that all previously moved notifications are located in the Viewed Notifications tab | all previously moved notifications are located in the Viewed Notifications tab | Passed |  |  | A.Shkurat | Not available |  | notifications are not in the database | A.Shkurat
AT |  | FUN: perform check for multiple clicks on a link | the desired deposit is opened | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: check that messages marked as read are displayed in a common frame | Messages are displayed in a common frame | Failed | QATC-675490 | messages are not displayed in the general frame | A.Shkurat | Not available |  | notifications are not in the database | A.Shkurat
AT |  | GUI: perform check that the link appearance changes on hover or click | link changes appearance | Failed | QATC-675501 | the appearance of the link does not change | A.Shkurat | Failed | QATC-675501 | the appearance of the link does not change | A.Shkurat
AT |  | GUI: check that the background color of the notification frame matches "gray" | background color of the notification frame matches "gray" | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: make sure that the text does not go beyond the working area of the notification | the text does not go beyond the working area of the notification | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: check link is underlined |  | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: check that there are no grammatical, syntactic and punctuation errors in the notification | text without error | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: make sure that the cursor changes its appearance when hovering over the link | the cursor changes | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: check that the notification frames has the same size | notification frames has the same size | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT | Fun: Upcoming Sessions | FUN: check the display of scheduled sessions | the system displays scheduled sessions | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: check the display of missed sessions | the system does not display missed sessions | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: check session information: number, date, time | "session information contains: session number, session time and date" | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: "check the clickability of the ""session date and time"" links" | "the date and time of sessions are displayed as links" | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | FUN: check the "session date and time" link for correct operation according to the specification | the "Schedule" tab is displayed in the system with an expanded tab for the specified "Session Date and Time" | Failed | QATC-677165 | the "date and time of the session" link redirects to a fully expanded schedule of all dates, and not to the schedule of the specified date. | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | GUI:Check the information in the "upcoming sessions" section for compliance with the specification | the section about upcoming sessions contains information: the word session, session number, full month, date, year, time. | Failed | QATC-677923 | coaching Year: 1 - not in the specification. | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI:check the date and time format | date and time format - full month, date, year, hours, minutes, am, Pacific time | Failed | QATC-677856 | the date and time format - month abbreviation, date, year, hours, minutes, seconds, AM- does not comply with the specification. | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: make sure that the cursor changes its appearance when hovering over the link | the cursor changes | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
Link: See Full Schedule
Smoke |  | FUN: check the link's clickability | the link is active, when clicked, the system redirects to the "full schedule" tab | Passed |  |  | A.Shkurat | Failed | QATC-677990 | the link is not active | A.Shkurat
MAT |  | FUN: check the correctness of the "full schedule" link based on the specification | the system displays the Schedule tab with the expanded section Upcoming session (specification item 34) | Failed | QATC-677411 | the application displays a collapsed section "upcoming session" when clicking on the link "full schedule". | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | FUN: perform check for multiple clicks on a link | the desired deposit is opened | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: make sure that the cursor changes its appearance when hovering over the link | the cursor changes | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT | Fun.: Pending Action Plans | FUN: look at the block Pending Action Plans, namely, on the dates to the right of the [Action Plan Names] | plans are sorted by date, starting from the nearest date | Failed | QATC-677308 | plans are sorted correctly, but the dates are incorrect | A.Shkurat | Not tested |  | the system is empty, there is nothing to check on | A.Shkurat
MAT |  | FUN: look at the block with dates, to the right of the [Action Plan Names] | the date is presented in the format MM/DD/YYYY | Passed |  |  | A.Shkurat | Not tested |  | the system is empty, there is nothing to check on | A.Shkurat
MAT |  | FUN: clicks a link with [Action Plan Name] | the Systems displays tab Action Plans with expanded inlay for the specified [Action Plan Name] | Failed | QATC-677314 | does not expanded inlay for the specified Action Plan | A.Shkurat | Not tested |  | the system is empty, there is nothing to check on | A.Shkurat
MAT |  | FUN: look at the block below the line "Pending Action Plans" | see three lines with one Action Plan each | Passed |  |  | A.Shkurat | Not tested |  | the system is empty, there is nothing to check on | A.Shkurat
MAT |  | FUN: check that each [Action Plan Names] is signed correctly | 1. click on link [Action Plan Name] 2. check the name with the plan opened in the tab Action Plans | Not tested |  | cannot be tested until bug QATC-677314 is fixed | A.Shkurat | Not tested |  | the system is empty, there is nothing to check on | A.Shkurat
AT |  | FUN: double click on the link [Action Plan Names] | the Systems displays tab Action Plans with expanded inlay for the specified [Action Plan Name] | Passed |  |  | A.Shkurat | Not tested |  | the system is empty, there is nothing to check on | A.Shkurat
MAT |  | GUI: check section title | section title is Pending Action Plans | Failed | QATC-677320 | extra word in title | A.Shkurat | Failed | QATC-677320 | extra word in title | A.Shkurat
MAT |  | GUI: look at the block below the line "Pending Action Plans" | [Action Plan Names] display as links, underlined text in blue | Failed | QATC-677323 | lines are underlined, but black. Should be blue | A.Shkurat | Not tested |  | the system is empty, there is nothing to check on | A.Shkurat
MAT |  | GUI: move cursor over link [Action Plan Names] | cursor changed to cursor-pointer | Passed |  |  | A.Shkurat | Not tested |  | the system is empty, there is nothing to check on | A.Shkurat
MAT |  | GUI: look at the block with dates, to the right of the [Action Plan Names] | text is black. Before the date the text "Date Due:" | Passed | QATC-677312 | dates are below the plans, not to the right | A.Shkurat | Not tested |  | the system is empty, there is nothing to check on | A.Shkurat
Link: See All Atcion Plans
MAT |  | FUN: clicks a link "See All Action Plans" | the Systems displays tab Action Plans with section Pending Action Plans expanded | Passed |  |  | A.Shkurat | Failed | QATC-677324 | link is not working | A.Shkurat
AT |  | FUN: double click on the link "See All Action Plans" | the Systems displays tab Action Plans with section Pending Action Plans expanded | Passed |  |  | A.Shkurat | Not tested |  | cannot be tested until bug QATC-677314 is fixed | A.Shkurat
MAT |  | GUI: move cursor over link "See All Action Plans" | cursor changed to cursor-pointer | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT |  | GUI: look at the line "See All Action Plans" | display as links, underlined text in blue | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT | Fun.: Recent Documents | FUN: check that the last modified documents are displayed | last modified documents are displayed | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
MAT |  | FUN: check that when you click on the name of the documents, you go to the corresponding page | сlicking on the title of a document will take you to the corresponding page | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
MAT |  | FUN: check that when clicking on the document modification date, there is no transition to other pages | when you click on the date of the document modification, there is no transition to other pages | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
MAT |  | FUN: check that when clicking on the document modification time, there is no transition to other pages | when you click on the time the document is being modified, there is no transition to other pages | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | FUN: perform check for multiple clicks on document name | the desired page opens | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
MAT |  | FUN: check that when clicking on the author of the document change, there is no transition to other pages | when clicking on the author of the document change, there is no transition to other pages | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check that when you hover over the document name, the cursor changes to a hand cursor | when you hover over the name of the document, the cursor changes to a hand cursor | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check that links to documents work only when clicking on the links themselves | links only works when you click on the links themselves and do not work when you click on the areas near the links | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check for grammatical errors | no grammatical errors | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check author's name format | the author's name is written inn the format: by: Name, Surname | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | CUI: check that the dates are in the same format | the date has the format: Lost modified: MM/DD/YYYY | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check that the time is in twelve-hour format | time in all sections is in twelve-hour format | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check if the section name matches the name in the specification | the section name is the same as the section name in the specification | Failed | QATC-675830 | the section name does not match the section name in the specification | A.Shkurat | Failed | QATC-675830 | the section name does not match the section name in the specification | A.Shkurat
AT |  | GUI: check that the date and time the documents were modified are displayed | the date and time the documents were modified is displayed | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check if the actual names of the documents match those displayed | the actual names of the documents are the same as those displayed | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check if the actual authors of the document change match those displayed | the actual authors of the document change are the same as those displayed | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check if the actual date of change and time of change match those displayed | the date and time of the last changes are the same as those displayed | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check that the color of the document name is blue | the document name color blue | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: check the document name is underlined | the document name underlined | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
AT |  | GUI: perform check that the document name appearance changes on hover or click | the document name changes appearance | Not tested |  | missing documents in the system | A.Shkurat | Not tested |  | missing documents in the system | A.Shkurat
Link: See All Documents
Smoke |  | FUN: check link functionality | сlicking on a link will take you to the corresponding tab | Not implemented | QATC-676571 | there is no link to See All Documents | A.Shkurat | Not implemented | QATC-676571 | there is no link to See All Documents | A.Shkurat
AT |  | FUN: perform check for multiple clicks on a link | the desired page opens | Not tested |  | no link | A.Shkurat | Not tested |  | no link | A.Shkurat
AT |  | GUI: check link title | the link has a name See All Documents | Not tested |  | no link | A.Shkurat | Not tested |  | no link | A.Shkurat
AT |  | GUI: check that the link works when clicking on the link itself | links only works when you click on the links themselves and do not work when you click on the areas near the links | Not tested |  | no link | A.Shkurat | Not tested |  | no link | A.Shkurat
AT |  | GUI: perform check that the link appearance changes on hover or click | link changes appearance | Not tested |  | no link | A.Shkurat | Not tested |  | no link | A.Shkurat
AT |  | GUI: make sure that when hovering over a link, the cursor changes to a hand cursor | when hovering over a link, the cursor changes to a hand cursor | Not tested |  | no link | A.Shkurat | Not tested |  | no link | A.Shkurat
AT |  | GUI: check for grammatical errors | no grammatical errors | Not tested |  | no link | A.Shkurat | Not tested |  | no link | A.Shkurat
AT |  | GUI: check that the color of the link is blue | link color blue | Not tested |  | no link | A.Shkurat | Not tested |  | no link | A.Shkurat
AT |  | GUI: check link is underlined | link underlined | Not tested |  | no link | A.Shkurat | Not tested |  | no link | A.Shkurat
Mod: Action plans
Smoke |  | FUN: perform check that Action plans tab is opened | tab is loaded correctly | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
Smoke |  | FUN: perform check that Action Plan Names are displayed | Action Plan Names are displayed | Passed |  |  | A.Shkurat | Failed | QATC-676523 |  | A.Shkurat
MAT |  | FUN: perform check that only users who logged-in have access to that tab | access has a logged-in user | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT |  | FUN: perform check that by default the list of Pending Action Plans is expanded and the list of Completed Action Plans is collapsed | by default the Pending Action Plans’ list is expanded and the Completed Action Plans’ list is collapsed | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT |  | FUN: perform check that lists collapse and expand | collapse and expand works | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check text height and width | the same height and width of the text of various elements of the same type | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check font consistency | all fonts of the same type elements is the same style | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform сheck text alignment | text is left aligned, the names of the field should be centered | Failed | QATC-677188 | the same error occurs in Mozilla browser | A.Shkurat | Failed | QATC-677188 |  | A.Shkurat
AT |  | GUI: perform check that the dates are in the same format | the date has the format: month/day/year | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: perform check the spelling of the tab name | tab name is spelled correctly | Failed | QATC-676511 | the same error occurs in Mozilla browser | A.Shkurat | Failed | QATC-676511 |  | A.Shkurat
MAT | Fun: Pending Action Plans | FUN: perform check that Action Plan Names are displayed as the links in ascending order by due date | names displayed in ascending order of date | Failed | QATC-675822 | the same error occurs in the Completed Action Plans tab | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: perform check that by clicking on the "Mark as Complete" button , the System moves Action Plan from Pending Action Plans’ list | the System moves Action Plan from Pending Action Plans’ list to Completed Action Plans’ list | Passed |  |  | A.Shkurat | Failed | QATC-676532 | the same error occurs in the Completed Action Plans tab | A.Shkurat
MAT |  | FUN: perform check that by clicking on the "Action Plan Name" link, The Systems displays inlay | the Systems displays inlay with detailed description for the Action Plan | Failed | QATC-675833 | the same error occurs in the Completed Action Plans tab | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: perform check if the dates are correct | the dates are correct | Failed | QATC-678348 |  | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: perform check that clicking on the entire area of ​​the "Mark as Complete" button should work, not just its name. | the click works on the entire button area | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | FUN: perform a check so that the link is triggered only when you click on the link itself, and not on an empty area next to it | the link only works when you click on it | Failed | QATC-675838 | the same error occurs in the Completed Action Plans tab in both browsers | A.Shkurat | Failed | QATC-675838 |  | A.Shkurat
AT |  | FUN: perform check for multiple clicks on a link | the desired deposit is opened | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | FUN: perform check that clicking the button quickly several times in a row | doesn't invoke the same action several times | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | FUN: perform check that clicking the space between closely located buttons | should not invoke any actions | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | FUN: perform check that clicking the space around the button | should not invoke any actions. | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check that the dates are in the same format | the date has the format: month/day/year | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: perform check for grammar, syntax and punctuation errors | text without error | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check that the button name is logical and is related to the action performed and does not contain grammatical errors | button name is spelled without errors. Performs a logical action | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check that cursor changes when hovering over a button | the cursor changes to a hand shape | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check that the UI of the button should change when clicked and when the cursor is hovered over it | UI of the button changed when clicked and when the cursor is hovered over it | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check that the description in the inlay does not go beyond the block border | eру description does not go beyond the block border | Not available |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: perform check that the link appearance changes on hover or click | link changes appearance | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check that cursor changes when hovering over a link | the cursor changes to a hand shape | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: check for cursor changes only when the cursor hovers over a link or button | the cursor should not change | Failed | QATC-676498 | the same error occurs in Mozilla browser | A.Shkurat | Failed | QATC-676498 |  | A.Shkurat
AT |  | GUI: perform check that buttons design is unified with the application design | the design is unified | Failed | QATC-676489 | the same error occurs in Mozilla browser | A.Shkurat | Failed | QATC-676489 |  | A.Shkurat
AT |  | GUI: perform check that links design is unified with the application design | the design is unified | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT | Fun: Completed Action Plans | FUN: perform check that Action Plan Names are displayed as the links in ascending order by due date | names displayed in ascending order of date | Failed | QATC-675822 |  | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: perform check that the action plans remain in the Completed plans tab | action plans should be saved in the Completed Action Plans tab | Failed | QATC-678369 |  | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: perform check that System binds current date of the server as Date Completed for the action plan | binds the correct current date of the server | Failed | QATC-676473 |  | A.Shkurat | Not available |  |  | A.Shkurat
MAT |  | FUN: perform check that by clicking on the "Action Plan Name" link, The Systems displays inlay | the Systems displays inlay with detailed description for the Action Plan | Failed | QATC-675833 |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | FUN: perform check so that the link is triggered only when you click on the link itself, and not on an empty area next to it | the link only works when you click on it | Failed | QATC-675838 |  | A.Shkurat | Failed | QATC-675838 |  | A.Shkurat
AT |  | FUN: perform check for multiple clicks on a link | the desired deposit is opened | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
MAT |  | FUN: perform check if the dates are correct | the dates are correct | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: perform check that the description in the inlay does not go beyond the block border | eру description does not go beyond the block border | Not available |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: perform check that cursor changes when hovering over a link | the cursor changes to a hand shape | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check that the link appearance changes on hover or click | link changes appearance | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check that the dates are in the same format | the date has the format: month/day/year | Passed |  |  | A.Shkurat | Not available |  |  | A.Shkurat
AT |  | GUI: perform check for grammar, syntax and punctuation errors | text without error | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat
AT |  | GUI: perform check that links design is unified with the application design | the design is unified | Passed |  |  | A.Shkurat | Passed |  |  | A.Shkurat